Sample chronogram for planning and management of CD

School and Community-based distribution – Activities plan

| # of Days | Dates | Tasks/Activities | Participants | Contact | Location | Facilitators |
| --- | --- | --- | --- | --- | --- | --- |
| Phase I: Planning and Rapid Assessment (14 days) |  |  |  |  |  |  |
| 1 |  | Preparatory meetings (Health and Education) to provide background and selection of sites: - Pre-meeting with officials (Key Education sector officials - Finalization of timelines | School (Health & Education) Community (Health) | NMCP |  |  |
| 2 |  | Interaction and review of reports, documents with key stakeholders leading to design of rapid assessment tools/checklist | School (Health & Education) Community (Health) | NMCP |  |  |
| 7 |  | Field-based assessment of existing structures in Communities, Education sector to National, sub-national and lower levels | School (Health & Education) Community (Health) | NMCP |  |  |
| 1 |  | Feedback meeting from the assessment teams | Key stakeholders | NMCP |  |  |
| 2 |  | Data entry and analysis of findings from assessment teams |  |  |  |  |
| 1 |  | Consensus and validation meeting with key stakeholders to present key findings from the assessment and brainstorm on best way forward, t | Key stakeholders | NMCP |  |  |
| Phase II – Development of ITN Continuous distribution strategy (4 days) |  |  |  |  |  |  |
| 3 |  | Develop draft ITN CD design strategy design |  |  |  |  |
| 1 |  | Stakeholders workshop on ITN CD strategy design document to finalize strategy | Key stakeholders | NMCP |  |  |
| Phase III: Implementation of ITN continuous distribution strategy; nationwide – (43 days – school CD) |  |  |  |  |  |  |
| 1 |  | Preparatory and planning meetings towards implementation of CD strategy | Key stakeholders | NMCP |  |  |
| 5 |  | Micro planning activities + production of data collection tools and BCC materials, based on micro planning data | Bottom up approach Validation by sub-national Approvals by National | NMCP |  |  |
| 4 |  | Training of trainers (TOT) workshop on data collection tools and BCC materials | Key stakeholders at national level | NMCP |  |  |
| 10 |  | Training of implementers at various levels – step down approach (clustered training) and feedback from cascade | Trainers | NMCP |  |  |
| 2 |  | Sensitization and mobilization of Parents Forum in all schools, community and religious leaders | Local authorities, ACSM officials | NMCP |  |  |
| 5 |  | Movement of LLINs from national CMS to lowest level stores | Logisticians | NMCP |  |  |
|  |  | Distributions: - Schools – selected classes (2 days) - Community – pull strategy based on request by households (continuous/year round) | NMCP |  |  |  |
| 3 |  | Data collation and aggregation | Lowest data generation point to national | NMCP |  |  |
| 4 |  | End process evaluation/ Net hanging | CHV | NMCP |  |  |
| 5 |  | Data entry and analysis of distribution | M&E officers | NMCP |  |  |
| 3 |  | Interim report writing and circulate draft report |  | NMCP |  |  |
| 1 |  | Presentation of preliminary results | Key stakeholders | NMCP |  |  |
| NB: Monitoring and supervision shall be jointly conducted by national and sub-national officials, (including education sector, if school-based) |  |  |  |  |  |  |