## Chronogramme FR
CHRONOGRAMME DES ACTIVITES DU PROJET PILOTE DE DISTRIBUTION DES MILDA EN MILIEU SCOLAIRE EN GUINÉE
Activités | Responsible | Outputs | Dissemination | Nov 20-26 | Nov 27-Dec3 | Dec 4-10 | Dec 11-17 | Dec 18-24 | Dec 25-31 | Jan 1-7 | Jan 8-15 | Jan 16-22 | Jan 23-29 | Jan 29-Feb 4 | Feb 5-11 | Feb 12-18 | Feb 19-25 | Feb 26-Mar4 | Mar 5-11 | Mar 12-18 | Mar 19-25 | Mar 26-Apr 1 | April 2-8 | April 9-15 | April 16-22 | April 23-29 | April 30-May 6 | May 7-13
Reunion du comité National de coordination | bar: Dec 18-24; Jan 8-15; Jan 23-29
Reunion du comité Prefectoral de coordination | bar: Dec 18-24; Jan 16-22
Finalisation du chronogramme des activites |  | Completed Timeline
Elaboration du plan de supervision |  | Final Plan | bar: Dec 4-10 to Dec 25-31
Elaboration du plan de communication |  | Final Plan | bar: Dec 4-10 to Dec 25-31
Elaboration du plan de formation |  | Final Plan | bar: Dec 4-10 to Dec 25-31
Finalisation du budget |  | Final Budget | bar: Dec 4-10 to Jan 16-22
Elaboration du plan logistique |  | Final Plan | bar: Dec 11-17 to Jan 16-22
Microplanification logistique |  | Final Plan
Elaboration des supports de formation |  | Materials | bar: Dec 11-17 to Jan 23-29
Elabortion des supports communication (SBCC) |  | Materials
1-Conception et Production de supports | bar: Dec 18-24 to Jan 1-7
2- Reprogrphie et diffusion
Finalisation des guides de mise en œuvre |  | Guidelines
Sensibilisation de la communauté/Reunion plaidoyer | bar: Jan 16-22 to Jan 23-29
Formation des formateurs (Comite pref&DSEE, CCS) |  | Report | [16 empty] | March 5-6 @ Conakry
Formation dans les zones d'intervention (Directeurs d'écoles,Présidents APEAE,COSAH,leaders réligieux et les volontaires du corps de la paix) |  | Report | [16 empty] | March 7-9/March 10-11
Transport des moustiquaires de Conakry à Boffa
Transport des moustiquaire de Boffa vers les Sites de distribution
Activités de communication pré-campagne
Campagne de communication
RETARD DE CAMPAGNE (LA GRÈVE DE L'ENSEIGNANT) - TROIS SEMAINES
Distribution des moustiquaires
Transport des reliquats de moustiquaires aux structures sanitaires
Activities de Communciation post campagne
Reportage
Revue nationale (restitution)
Revue prefectorale apres la mise en oeuvre
Soumission du protocole d'enquete au comité d'ethique | bar: Dec 25-31 to Jan 23-29
Formation des enqueteurs
Enquête finale | [28 empty] | * To be completed by May 20
Analyse de données | [28 empty] | * To be completed by June 10
Plan Dissemination | [28 empty] | *Will be moved to June/July after analysis has been completed
Rencontre de Dissemination | [28 empty] | *Will be moved to June/July after analysis has been completed
Notes: Du 13 -19 février seront réservés pour regrouper et s'assurer que tous les outils sont complets
Note on A21: Charles Keamou Thea: Reunir qu niveau national les formateurs, uniformiser les outils

## Sheet1
GUINEA MILDA DISTRIBUTION AU MILIEU DE SCOLAIRE CHRONOGRAM
Activity | Responsible | Outputs | Dissemination | Nov 20-26 | Nov 27-Dec3 | Dec 4-10 | Dec 11-17 | Dec 18-24 | Dec 25-31 | Jan 1-7 | Jan 8-15 | Jan 16-22 | Jan 23-29 | Jan 30-Feb 5 | Feb 6-12 | Feb 13-19 | Feb 20-26 | Feb 27-Mar 5 | Mar 6-12 | Mar 13-19 | Mar 20-26 | Mar 27- Apr 2 | April 3 -9 | April 10-16 | April 17-23 | April 24-30 | May 1-7 | May 8-14
National Coordination Committee | bar: Dec 18-24; Jan 8-15; Jan 23-29
Local Coordination Committee | bar: Dec 18-24; Jan 16-22
Finalize Timeline | Sean | Completed Timeline
Develop Supervision Plan |  | Final Plan | bar: Dec 4-10 to Dec 25-31
Communications Plan |  | Final Plan | bar: Dec 4-10 to Dec 25-31
Training Plan |  | Final Plan | bar: Dec 4-10 to Dec 25-31
Finalize Budget |  | Final Budget | bar: Dec 4-10 to Jan 16-22
Microplanning |  | Final Plan | bar: Dec 11-17 to Jan 16-22
Logistics Plan |  | Final Plan
Create Training Materials |  | Materials | bar: Dec 11-17 to Jan 23-29
Develop SBCC Materials |  | Materials
Final Implementation Guidelines |  | Guidelines
Initial Community Sensitization | bar: Jan 16-22 to Jan 23-29
Training of Trainers |  | Report
Prefectural Training |  | Report
Training of School Directors |  | Report
Movement of nets to DSEE
Movement of nets to schools
Pre campaign communication activities
Campaign communication activities
Net Distribution
Remaining Nets to Health Facilities
Post campaign communciation activities
Reporting
Post Action Review National
Post Action Review Local
IRB Preparation/Submission | bar: Dec 25-31 to Jan 23-29
Survey Training
Endline Survey
Analysis
Plan Dissemination Event
Dissemination Event
Notes: Feb 13-19 will be reserved for bundling and making sure all tools are complete