## YR2
VectorWorks Tanzania
Year 2: Oct 2015- Sept 2016
|  |  |  | MONTH 1 (OCT'15) |  |  |  | MONTH 2 (NOV'15) |  |  |  | MONTH 3 (DEC'15) |  |  |  | MONTH 4 (JAN'16) |  |  |  | MONTH 5 (FEB'16) |  |  |  | MONTH 6 (MAR'16) |  |  |  | MONTH 7 (APR'16) |  |  |  | MONTH 8 (MAY'16) |  |  |  | MONTH 9 (JUN'16) |  |  |  | MONTH 10 (JUL'16) |  |  |  | MONTH 11 (AUG'16) |  |  |  | MONTH 12 (SEP'16)
|  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Activity | Tasks & Deliverables |  | Lead Partner
Health Facility - Based (ANC & EPI) LLINs Distribution
PC.2 Preparatory activities | TASKS | Meeting with national level stakeholders on health facility - based LLINs distribution approach | bar: MONTH 2 (NOV'15) 3 to MONTH 2 (NOV'15) 4
Formulation of national orientation and monitoring team | bar: MONTH 2 (NOV'15) 4
Development of guidelines and tools for health facility - based LLINs distribution | bar: MONTH 1 (OCT'15) 1 to MONTH 1 (OCT'15) 4
Receive preliminary response/feedback from PMI on the development of guidelines and tools for health facility - based LLINs distribution | bar: MONTH 2 (NOV'15) 2
Review the guidelines with stakeholders (numerous) | bar: MONTH 2 (NOV'15) 4
Finalization of the guidelines and tools for health facility- based distribution | bar: MONTH 2 (NOV'15) 4
Developmenet of training manual for health facility- based distribution | bar: MONTH 2 (NOV'15) 3 to MONTH 2 (NOV'15) 4
Development of accountability information system for LLINs distribution | bar: MONTH 2 (NOV'15) 3 to MONTH 2 (NOV'15) 4
Planning to sustain LLINs coverage in the 7 PMI regions
| DELIVERABLES | National orientation & monitoring team in place
Training manual, guidelines and tools developed
Accountability information system for LLINs distribution isin place
IM.7 BCC and social mobiization | TASKS | Determine fundinng and posponsible entity for BCC | bar: MONTH 2 (NOV'15) 1
Develoment and design of health facility- based BBC strategy | bar: MONTH 2 (NOV'15) 2 to MONTH 2 (NOV'15) 3
Testing and approval of BCC strategy, message and materials | bar: MONTH 2 (NOV'15) 4 to MONTH 3 (DEC'15) 1
Production of BCC materials | bar: MONTH 3 (DEC'15) 1
Deployment of BCC and mobilization strategy | bar: MONTH 3 (DEC'15) 2 to MONTH 5 (FEB'16) 4
| DELIVERABLES | BCC and mobilization stategy in place
Deployment of BCC and mobilization strategy
ANC/EPI - Mtwara Region
IM.8 Data Collection | TASKS | Quantification of annual LLINs need for ANC & EPI channes for each district and facility | bar: MONTH 2 (NOV'15) 1 to MONTH 2 (NOV'15) 2
Verification of annual LLINs need for ANC & EPI channes for each district and facility | bar: MONTH 2 (NOV'15) 3 to MONTH 2 (NOV'15) 4
| DELIVERABLES | Quantification report
Verification report
IM.9 Trainings and orientations | TASKS | National Level TOT | bar: MONTH 3 (DEC'15) 1 to MONTH 3 (DEC'15) 2
Regional & District Orientation & Planning Meeting | bar: MONTH 4 (JAN'16) 2 to MONTH 4 (JAN'16) 3
Training of Health workers in Health Facilities | bar: MONTH 4 (JAN'16) 3 to MONTH 4 (JAN'16) 4
| DELIVERABLES | Training reports
IM.10 Logistics and supply chain | TASKS | Transport of ITN from National level to Zonal MSD | bar: MONTH 4 (JAN'16) 4 to MONTH 5 (FEB'16) 1
Initial supply of ITN from Zonal MSD to Health Facilities | bar: MONTH 5 (FEB'16) 2 to MONTH 5 (FEB'16) 3
Restocking of ITN to Health Facilities from Zonal MSD | bar: MONTH 8 (MAY'16) 4 to MONTH 9 (JUN'16) 1; MONTH 12 (SEP'16) 2 to MONTH 12 (SEP'16) 3
| DELIVERABLES | Report on LLIN transportation from MSD to zonal and facility
Restocking report
ME.3 Monitoring and supervision | TASKS | Project Level Monitoring of Field Activities | bar: MONTH 3 (DEC'15) 1 to MONTH 12 (SEP'16) 4
Monitoring of Trainings | bar: MONTH 3 (DEC'15) 1 to MONTH 3 (DEC'15) 2; MONTH 4 (JAN'16) 2 to MONTH 4 (JAN'16) 4
Initial Intensive Monitoring of Health Facility ITN Distribution | bar: MONTH 5 (FEB'16) 2 to MONTH 5 (FEB'16) 4
Routine Monitoring of Health Facility-based ITN Distribution | bar: MONTH 6 (MAR'16) 1 to MONTH 12 (SEP'16) 4
| DELIVERABLES | Monitoring reports
IM.11 Accountability, Reporting & Review Meetings | TASKS | Submission of Data to District Level by All Health Facilities | bar: MONTH 6 (MAR'16) 1; MONTH 7 (APR'16) 1; MONTH 8 (MAY'16) 1; MONTH 9 (JUN'16) 1; MONTH 10 (JUL'16) 1; MONTH 11 (AUG'16) 1; MONTH 12 (SEP'16) 1
Submission of Reports to Regional Level by All Districts | bar: MONTH 6 (MAR'16) 2; MONTH 7 (APR'16) 2; MONTH 8 (MAY'16) 2; MONTH 9 (JUN'16) 2; MONTH 10 (JUL'16) 2; MONTH 11 (AUG'16) 2; MONTH 12 (SEP'16) 2
Submission of Reports to National Level by Region | bar: MONTH 6 (MAR'16) 3; MONTH 7 (APR'16) 3; MONTH 8 (MAY'16) 3; MONTH 9 (JUN'16) 3; MONTH 10 (JUL'16) 3; MONTH 11 (AUG'16) 3; MONTH 12 (SEP'16) 3
Regional Review Meetings | bar: MONTH 5 (FEB'16) 4; MONTH 6 (MAR'16) 4; MONTH 9 (JUN'16) 4; MONTH 12 (SEP'16) 4
| DELIVERABLES | Data reports
Review meetings reports
ANC/EPI - Mwanza Region
IM.8 Data Collection | TASKS | Quantification of annual LLINs need for ANC & EPI channes for each district and facility | bar: MONTH 4 (JAN'16) 2 to MONTH 4 (JAN'16) 3
Verification of annual LLINs need for ANC & EPI channes for each district and facility | bar: MONTH 4 (JAN'16) 4 to MONTH 5 (FEB'16) 1
| DELIVERABLES | Quantification report
Verification report
IM.9 Trainings and orientations | TASKS | Regional & District Orientation & Planning Meeting | bar: MONTH 6 (MAR'16) 1 to MONTH 6 (MAR'16) 2
Training of Health workers in Health Facilities | bar: MONTH 6 (MAR'16) 3 to MONTH 6 (MAR'16) 4
| DELIVERABLES | Training reports
IM.10 Logistics and supply chain | TASKS | Transport of ITN from National level to Zonal MSD | bar: MONTH 7 (APR'16) 1 to MONTH 7 (APR'16) 3
Initial supply of ITN from Zonal MSD to Health Facilities | bar: MONTH 7 (APR'16) 4 to MONTH 8 (MAY'16) 1
Restocking of ITN to Health Facilities from Zonal MSD | bar: MONTH 11 (AUG'16) 2 to MONTH 11 (AUG'16) 3
| DELIVERABLES | Report on LLIN transportation from MSD to zonal and facility
Restocking report
ME.3 Monitoring and supervision | TASKS | Project Level Monitoring of Field Activities | bar: MONTH 5 (FEB'16) 2 to MONTH 12 (SEP'16) 4
Monitoring of Trainings | bar: MONTH 5 (FEB'16) 2 to MONTH 6 (MAR'16) 1
Initial Intensive Monitoring of Health Facility ITN Distribution | bar: MONTH 7 (APR'16) 4 to MONTH 8 (MAY'16) 1
Routine Monitoring of Health Facility-based ITN Distribution | bar: MONTH 8 (MAY'16) 2 to MONTH 12 (SEP'16) 4
| DELIVERABLES | Monitoring reports
IM.11 Accountability, Reporting & Review Meetings | TASKS | Submission of Data to District Level by All Health Facilities | bar: MONTH 8 (MAY'16) 2; MONTH 9 (JUN'16) 2; MONTH 10 (JUL'16) 2; MONTH 11 (AUG'16) 2; MONTH 12 (SEP'16) 2
Submission of Reports to Regional Level by All Districts | bar: MONTH 8 (MAY'16) 3; MONTH 9 (JUN'16) 3; MONTH 10 (JUL'16) 3; MONTH 11 (AUG'16) 3; MONTH 12 (SEP'16) 3
Submission of Reports to National Level by Region | bar: MONTH 8 (MAY'16) 4; MONTH 9 (JUN'16) 4; MONTH 10 (JUL'16) 4; MONTH 11 (AUG'16) 4; MONTH 12 (SEP'16) 4
Regional Review Meetings | bar: MONTH 8 (MAY'16) 1; MONTH 9 (JUN'16) 1; MONTH 12 (SEP'16) 1
| DELIVERABLES | Data reports
Review meetings reports
Note on D15: Waziri Nyoni: This activity was not clear in the work plan