School-based Continuous LLIN distribution in Shomolu LGA, Lagos State

Micro planning Workshop for Principals, District II and State Ministry of Education Officials - 6th February, 2015

AGENDA:

| TIME | ACTIVITY | RESPONSIBLE |
| --- | --- | --- |
| 10.00am - 10.10am | Setting the stage (opening prayer, self-introductions and ground rules) | District II |
| 10.10am - 10.15am | Welcome Remarks | AD (BES) |
| 10.15am - 10.20am | Meeting Objectives Overview of SuNMaP | SuNMaP |
| 10.20am-11.00am | Overview of School-based distribution of LLIN and summary of field assessment results | Consultant |
| 11.00am - 11.30am | Tea/Coffee break | All |
| 11.30am-11.50am | Presentation on the micro planning template | Consultant |
| 11.50pm-2.00pm | Group work – using the micro plan template, quantification analysis of LLINs by class by schools in Shomolu LGA (numbers of students and teachers per class – JS 1 and SS 1) | All |
| 2.00pm-3.00pm | Lunch Break | All |
| 3.00pm-4.30pm | Plenary: Group presentation, finalization and validation of micro planning quantifications by school – lead by Principals, District II – Health focal person | Principals District II |
| 4.30pm - 4.40pm | Review of school distribution implementation plans – daily expectations | AD(BES), District II, SuNMaP |
| 4.40pm – 4.50pm | Discussions | All |
| 4.50pm – 5.00pm | Next Steps and Closing formalities | SuNMaP |
| 5.00pm | Departure | All |

Objectives:

- Quantification analysis of LLINs and materials by schools and by LGAs

- Discuss and agree on roll out of BCC backbone for the school-based program

- Establish stakeholders’ roles and responsibilities

- Share detailed implementation plans/timelines for distribution

SCHOOL-BASED DISTRIBUTION OF LLIN TO PUPILS/STUDENTS IN SHOMOLU LGA, LAGOS STATE

IMPLEMENTATION PLAN/ACTIVITY TIMELINES

| # of Days | Dates | Tasks/Activities | Participants | Contact(s) |
| --- | --- | --- | --- | --- |
| 3 | 4/02/2015 – 6/02/2015 | Micro planning activities + production of data collection tools and BCC materials, based on micro planning data | State and LGA teams (health & education), District II, SUBEB, 19 Principals, 48 Head Teachers, Partners | SuNMaP, Ind. Monitors NC, SC |
| 4 | 9/92/2015 – 12/02/2015 | Training of trainers workshop on data collection tools and BCC materials | State Health State Education PHC Board rep. District II, SUBEB, LGEA Desk Officer MOH Team Independent monitors | SuNMaP, NC, SC |
| 3 | 16/02/2015 – 18/02/2015 | Training of Principals/Head Teachers in the LGA (clustered training) and feedback from cascade | 19 Vice Principals and 48 Health Teachers | State/LGA teams, District, SUBEB, IMs, Monitors |
| 3 | 19/02/2015 21/02/2015 | Support training of teachers (primary and secondary) in all schools in the LGA and feedback from cascade | Form Teachers Class Teachers | VPs, Health Teachers, IMs, Monitors |
| 2 | 23/2/2015 – 24/02/2015 | Meetings of Parent Teachers Association (PTA)/ Parent Forum, in all schools in the LGA and sensitization of community/religious leaders in the LGA | PTA/Parent Forum Community/religious leaders, CSOs | LGA team (H&E) |
| 1 | 24/02/2015 | Movement of LLINs from State CMS to LGA warehouse (health store) | State and LGA Logisticians | SuNMaP, State Los. |
| 4 | 25/2/2015 – 28/2/2015 | Movement of LLINs from LGA warehouse to all Schools in the LGA | LGA Logisticians | SuNMaP, LGA (H-Log) |
| 1 | 3/3/2015 | LGA Flag off by the Hon. Commissioners for Health and Education | Top State MOH and MOE officials, TG/PS, PHC Board, Ex. Chairman – SUBEB, LGEA team, MOH | State team (Health & Education), SuNMaP |
| 2 | 3/3/2015 – 4/3/2015 | Distribution of LLINs to pupils and student (Pry 1, Pry 4, JS1 and SS1) in the LGA | Pupils/students | Principal/Head Teachers, LGA/ State team Ind. Monitors SuNMaP, NC, SC |
| 3 | 5/3/2015 – 7/3/2015 | Data collation and aggregation | Head teachers Class teachers | District II-DD LGEA Edu. Sec., HOS |
| 4 | 6/3/2015 – 9/3/2015 | End process evaluation/ Net hanging | Independent monitors | SuNMaP, NC, SC |
| 5 | 10/3/2015 – 14/3/2015 | Data entry, analysis of distribution and report | Data entry clerks | Ind. Monitors, NC, SC |
| 1 | 24/3/2015 | Presentation of preliminary results | Top State and LGA teams (H&E), District-II, Partners | SuNMaP |